## Slide 1
Professor:
Nathan White
nathan.white@cwu.edu
Students:
Max Shuford
Esther Law
Harrison Ingram-Bate
Alan Ruelas-Cordova
Parker Miller
Cruz Gonzalez
Moogle Gaps
Date: 01/24/2026
Key Risks and Issues:
Key Contacts
Project Objectives:
Develop an application that displays a map centered in the user's current location.
Enable users to enter two U.S. cities and receive driving directions.
Provide secure user authentication, allowing users to create accounts and log in safely.
Allow authenticated users to save up to five favorite routes.
M
Risk
Schedule
Project
Status
Key Milestones:
Complete the initial Software Requirements Specification (SRS).
Status Report 3
Major Tasks Planned for Next Two Weeks:
CS 480
Winter 2026
Date | Hours | Student(s) | Accomplishment
1/21/26 | 10 | Esther, Harrison, Alan, Parker, and Cruz | Brainstorming and listing Possible Use-Cases, grouping small use-cases into larger more general use cases.
1/22/26 | 2 | Max | Finalized Updated Schedule for Updated Project Plan.
1/22/26 | 1 | Max and Harrison | Reviewed and submitted Updated Project Plan.
Milestone | %Complete | Planned | Completed
Project Plan | 100% | 1/16/2026 | 1/15/2026
Updated Project Plan | 100% | 1/23/2026 | 1/22/2026
SRS | 10% | 2/6/2026 | -
Updated SRS | 0% | 2/13/2026 | -
Design Document | 0% | 2/27/2026 | -
Test Plan | 0% | 3/6/2026 | -
Working System | 0% | 3/13/2026 | -
Test Report | 0% | 3/13/2026 | -
Presentation | 0% | 3/16/2026 | -
Risk: | Risk Summary:
Issue: Meeting in person at a designated time. | Issue Summary & Resolution: Virtual meetings, and distance communication.
Key Accomplishments: