## Slide 1
Professor:
Nathan White
nathan.white@cwu.edu
Students:
Max Shuford
Esther Law
Harrison Ingram-Bate
Alan Ruelas-Cordova
Parker Miller
Cruz Gonzalez
Moogle Gaps
Date: 01/16/2026
Key Risks and Issues:
Key Contacts
Project Objectives:
Develop an application that displays a map centered in the user's current location.
Enable users to enter two U.S. cities and receive driving directions.
Provide secure user authentication, allowing users to create accounts and log in safely.
Allow authenticated users to save up to five favorite routes.
M
Risk
Schedule
Project
Status
Key Milestones:
Update Gantt chart to be in compliance with requirements.
Complete the Updated Project Plan based on instructor feedback.
Complete the initial Software Requirements Specification (SRS).
Status Report 2
Major Tasks Planned for Next Two Weeks:
CS 480
Winter 2026
Date | Hours | Student(s) | Accomplishment
1/9/26 | 12 | All Students | Completed purpose, scope of the project, references, and some of the glossary in the project plan..
1/13/26 | 8 | Esther, Harrison, Alan, and Cruz | Completed the milestones, assumptions, and constraints for the project plan.
1/14/26 | 12 | All Students | Completed risk table for the project plan. Started on phase descriptions, and tasks/effort table.
1/15/26 | 8 | Max | Completed the Gantt chart, embedded it into the Project Plan, and finalized the task/effort table and resources table.
1/15/26 | 2 | Esther and Harrison | Finalized the phase descriptions.
1/15/26 | 1 | All Students | Reviewed/Finalized and Submitted Project Plan.
Milestone | %Complete | Planned | Completed
Project Plan | 100% | 1/16/2026 | 1/15/2026
Updated Project Plan | 0% | 1/23/2026 | -
SRS | 0% | 2/6/2026 | -
Updated SRS | 0% | 2/13/2026 | -
Design Document | 0% | 2/27/2026 | -
Test Plan | 0% | 3/6/2026 | -
Working System | 0% | 3/13/2026 | -
Test Report | 0% | 3/13/2026 | -
Presentation | 0% | 3/16/2026 | -
Risk: | Risk Summary:
Issue: Meeting in person at a designated time. | Issue Summary & Resolution: Virtual meetings, and distance communication.
Key Accomplishments: